## Projects
| Apps | About
1 | Beacon Ecommerce | Beacon trade own products ecommerce application where beacon will sale his own products
2 | BuyHhour (Marketplace) | Here are two sections one for product and another for services , where multivendor can sale their product , and services
3 | Security App | This app will be used for soceity ,IT Corporations and Industries , Here here will be two end , one for resident, employees ,worker , staff and another end for security or Reception
4 | Job Search App | Here employers and employees will register and find thier resumes and post thier requirments,
5 | Bexall Common App | This is common app , Main app where this 4 app will show for navigations , and other common functions will be here , like wallet
6 | Barcode scanner app | This app for scan product barcode on location and dispatch for deliver the products
| Web (Backend) | About
1 | Beacon ERP | This is beacon erp where beacon will add inventory, sales purchase, and it is connected with beacon ecommerce app
2 | Security App Admin and Super Admin | There will be two backend to manage secuity app, one for super admin to add society and companies and another for society induvisual login to register their members and residents
3 | Marketplace SuperAdmin | From Where admin register vendors and manage theirs products and sales
4 | Marketplace Vendor Login | This is single vendor login, from where vendor can add their inventory and find sales (online and offline)
5 | Marketplace Service Provider admin | This is for service provider Login
6 | Job Portal Admin | This admin for manage job protal backend work
7 | Beacon CRM | This software for beacon enquiry and manage their staff work management
8 | Super Common Panel | Here all backend link will be connected for easy navigations

## Beacon Ecommerce
Beacon Ecommerce
| Features | Work Status
1 | Product Group and Category | done
2 | Product Segements | done
3 | Product List | done
4 | Product Single Page with information | done
5 | Add to cart | done
6 | Checkout | done
7 | Biilling | done
8 | Pincode Management | done
9 | Customer Group wise Discount Management | done
10 | Order Processing | done
11 | COD | done
12 | Payment Gateway | Pending
13 | Search Functionality | done
14 | Order History | done
15 | Order Cancellation and Return | done
16 | Customer Profile | done
17 | Sign in ¦ Sign up and Logout | done
18 | Products Review and Rating | done
19 | Products Questionnier | done
20 | Related products ¦ add on accessory connectivity | done
21 | Order Status Tracking | done

## ERP
ERP
| Features | Work Status
1 | Dashboard | done
2 | Masters | done
3 | Warehouse Management | done
4 | Vendor Creation | done
5 | Customer Creation | done
5 | Inventory Module | done
6 | Purchase ORder | done
7 | GRN | done
8 | Offline Sales | done
9 | Tax Invoices | done
10 | Performa Invoices | done
11 | Product Barcode Printing | done
12 | Stock Report | done
13 | Stock Report Summary Sales and Purchases wise | done
14 | Product Location and Dispatch Tracking | done
15 | Sale Report | done
16 | Purchase Report | done
17 | USers Module its right wise | done
18 | Ecommerce Connection | done
19 | Ecomerce Sale | done
20 | Ecommerce Enquiry | done
21 | Product Reviews and Rating | done
22 | Related Products | done
21 | Pincode Management | done
22 | Product Questinnaier | done
23 | App Slider and Banner Management | done
24 | Customer Group Creation | done
25 | Discount Management | done
26 | Online Sales Reports | done
27 | Online Sales Real Stock Connections | done
.......
| ....... | Working Continue (Need to Clearification for next module and updates, like payments , ledger , and account part erc)

## BuyNHour MarketPlace
| BuyNHour Marketplace App |  |  | BuyNHour Super Admin |  |  |  | Vendor Login
| Features | Work Status |  | Features | Work Status |  |  | Features | Work Status
1 | Product Category and Sub category | done | 1 | Dashboard | Pending |  | 1 | Dashboard | Pending
2 | Near by shops location wise | done | 2 | Masters | done |  | 2 | Common Product Inventory | done
3 | Service Category | done | 3 | Products Segment | done |  | 3 | Vendor Inventory | done
4 | Near By Service Provider wise | done | 4 | PRoduct Category and Sub Category | done |  | 4 | Stock In transfer | done
5 | Popular Category | done | 5 | Product Shop/Vendor Creation with login details | done |  | 5 | Wallet | done
7 | Product Segment | done | 6 | Markup geofencing on map for vendor area | done |  | 6 | Offline Sales | done
8 | Segment Wise shop listing | done | 7 | Common Inventory Creation | done |  | 7 | Customers Creation | done
9 | Category wise product listing | done | 8 | Service Segment | done |  | 8 | Online Sales Report | done
10 | Product single page with information | done | 9 | Service Provider Add | done
11 | On Product Vendor selection from where he/she want to buy | done | 10 | Markup geofencing on map for service provider area | done
12 | add to cart | done |  | ......
13 | Checkout | done | [5 empty] | (Working Continuee (Further functionality clearification required)
14 | billing | done |  | (Working Continuee (Further functionality clearification required)
15 | Order processing | done
16 | Payment Gateway | pending |  |  |  |  | Service Provider Panel
17 | Search Functionality | done
18 | Segment wise service provder listing | done |  |  |  |  | Features | Work Status
19 | Category wise service provider listing | done |  |  |  | 1 | Dashboard | Pending
20 | Service Booking | done |  |  |  | 2 | Wallet | Done
21 | Order history | done |  |  |  | 3 | Booking | Done
22 | Service Booking History | done |  |  |  | 4 | Booking Details | Done
23 | ORder cancellation | pending
24 | Service Booking Payment Settlement | pending
25 | Location Selection | done
......
| ...... | (Working Continuee (Further functionality clearification required)

## Secuity App
| Security App Resident Login |  |  | Security App Login |  |  | Security Super Admin
| Features | Work Status |  | Features | Work Status |  | Features | Work Status
1 | Waiting Entries for accept and reject | done | 1 | Visitor Entry | done | 1 | Dashboard | pending
2 | Entries logs | done | 2 | Scan Qr Code | done | 2 | Masters | done
3 | Pre approval Entry and qr sending option | done | 3 | Entry Tracking | done | 3 | Client Creations | done
4 | Vehicle Creation | done | 4 | In Out for visitor | done | 4 | Society Structure creation | done
5 | Member Adding option | done | 5 | Car Entry | done | 5 | Flat/Offices/Units Creations | done
9 | Concierge | done | 6 | Staff/Member Entry | done | 7 | Secutiry Guard Creation | done
10 | Complain | done | 7 | Emergency lookup | done | 8 | Client Admin user creation | done
11 | Notification | done | 8 | Concieirge | done | 9 | Resident users | done
12 | Raise alarm to security for emergency | done
Secutiry Company Login (IT ¦ Society ¦ Industry Different Login)
[6 empty] | 1 | Dashboard | done
[6 empty] | 2 | Structure Creation | done
[6 empty] | 3 | Unit Creation | done
[6 empty] | 4 | Security Creation | done
[6 empty] | 5 | Resident Creation | done
[6 empty] | 6 | Attendance Report | done
[6 empty] | 7 | Attendance Sheet | done
[6 empty] | 8 | Complain Box | done

## Dispatch Barcode Scan App
done
Barcode Scanner App
| Features | Work Status
1 | Invoice List | done
2 | Location Scan | done
3 | Dispatch Scan | done
4 | Warehouse location show | done
5 | Manual barcode entry | done
6 | Order Dispatch completion | done

## Jobs App
Jobs App
| Features | Work Status
1 | Category and sub category | done
2 | Job Listing | done
3 | Apply on Job | done
4 | Contact to job provider | done
5 | Upload Resumes | done
6 | Near by Jobs | done
7 | Applied Jobs Listing | done
8 | Post Job | done
9 | Tracking job application | done
10 | Applied job user cotacts and find resumes | done
11 | Search Jobs | done